## Sheet1
TECH TASKS	Build / (KURT)	Map Menu / (KURT)	Info Menu / (JEFF)	Game / (KURT)	Sound / (JEFF)	Finished
LEGEND / Red = High Priority / Orange = Medium Priority / Yellow = Low Priority / Green = Complete	Make sure game runs perfectly on demo computers.(First week of sept meeting)	Map screen idles after player inactive for 3 ? seconds(may need to adjust amount of time a lot until feels right) regions will begin to automatically pop up just a bit as a hint for player to click them....	Replace: "button_info_mesh" with "InfoIcon.tga" sprite. / Replace: "button_return_mesh" with "ReturnIcon.tga" sprite. / Replace: "button_direction_mesh_Left" with "NextIcon.tga" sprite.	Have the "Level script" look up the conservation variable I set per antelope (antelope card defs are in: prefab/carddefs/). Change the probability of which antelopes appear in the match based on this.	Implement all game sounds. / 75%	Allow for Easy Normal and Hard pictures to represent each level instead of photos on level select.
	Android		Fix alignment of info menu last column of cards(It has more empty space than the other columns).	Have the probability of lioness not be randomized and instead if lioness is in the array of elements for a level, simply add that many.		Fix antelope mislabled (may be related to duplicating).
	PC		Fix back button from playing sound instead of going to previous menu.	Matching Lioness(Clicking on 2 lioness) causes the player to imediately lose the match.		Fix all cards dissapear after clicking to left and right fast. Also sometimes they hang in half rotation.
	Web		Disable antelope name getting spoken again when going to new antelope.	Add main settings menu with audio options: voices, music, sfx. Video settings: TBA		Replace health counter UI with images provided.
	iOS		Add gender icon to each antelope card on the main info menu as well.			Fix order of antelopes appearing to be alphabetical.
			Prevent antelope sliding unexpectedly in and out of screen after clicking too fast.			Set antelopes to switch (for when the player clicks to right or left page)after card is half done rotating.
			Prevent long name from being clipped, like slender horned gazelle			Set up an "antelope" sound for missing antelope names.
						Add a new difficulty mode, "Baby"
						Allow the player to click anywhere on the screen(except for the back button) to see the antelope reer up and hear David.