## Sheet1
TECH TASKS	Build / (KURT)	Other / (MATT)	Info Menu / (JEFF)	Game / (KURT)	Sound / (JEFF)	Finished
LEGEND / Red = High Priority / Orange = Medium Priority / Yellow = Low Priority / Green = Complete	Make sure game runs perfectly on demo computers.(First week of sept meeting)	info button font design to be a blend of Will's 2 images.	Disable player control until info page is Completely ready(after antelope is in the screen center and map shown). Many different bugs seem to happen if pressing back before this transition.	Add main settings menu GUI.	Implement all game sounds. / 75%	Allow for Easy Normal and Hard pictures to represent each level instead of photos on level select.
	Add RBI logo to start of app after it says made by unity.	Back button in game is too far off to the side.	Prevent antelope appears on the screen for a second, then dissapears before walking into the center. Only happens the first time when clicking on any antelope of info menu.	Add credits page in main settings menu		Fix antelope mislabled (may be related to duplicating).
			Set antelopes to be the correct size.	Lioness stays after turning over bug		Fix all cards dissapear after clicking to left and right fast. Also sometimes they hang in half rotation.
			Prevent antelope sliding unexpectedly in and out of screen after clicking too fast.	Lioness match wins game instead of losing		Replace health counter UI with images provided.
			Replace: "button_info_mesh" with "InfoIcon.tga" sprite. / Replace: "button_return_mesh" with "ReturnIcon.tga" sprite. / Replace: "button_direction_mesh_Left" with "NextIcon.tga" sprite.	Add quit for pc build to main settings menu		Fix order of antelopes appearing to be alphabetical.
				Map screen idles after player inactive for 3 ? seconds(may need to adjust amount of time a lot until feels right) regions will begin to automatically pop up just a bit as a hint for player to click them....		Set antelopes to switch (for when the player clicks to right or left page)after card is half done rotating.
						Set up an "antelope" sound for missing antelope names.
						Add a new difficulty mode, "Baby"
						Allow the player to click anywhere on the screen(except for the back button) to see the antelope reer up and hear David.
08/04/18						Have the "Level script" look up the conservation variable set per antelope (antelope card defs: prefab/carddefs/). Change the probability of rare antelopes appearing in the match based on this so it may skip being added.
						Have the "Level script" for lioness be absolute probability rather than based on conservation status.
						Fix alignment of info menu last column of cards(It has more empty space than the other columns).
						Fix back button from playing sound instead of going to previous menu.
						Disable antelope name getting spoken again when going to new antelope.
						Add main settings menu with audio options: voices, music, sfx.
						Add another card def list just for lioness.
						Prevent long name from being clipped, like slender horned gazelle
08/18/18						PC
						Card Def Skip probability bug. If the first antelope listed is crittically endangered and second listed is least concern, it will always still pick the first listed.
						Card Def "Never Skip" bug. If lioness is lower in the list, the first antelopes in the list are always still picked instead.
						Matching Lioness(Clicking on 2 lioness) causes the player to imediately lose the match.
08/27/18						Replace the layout of the current info page to be like the "InfoPage_DayB.jpg" concept (\CardMatchingGame\DesignDocuments\Concepts\).
						Instead of male and female cards, just have one to select on the main info menu.
						Slow down the antelope mismatch wait time.

09/01/18