## Sheet1
	ART TASKS	% DONE	TIME ESTIMATE	TECH REQUIRED	% DONE	TIME ESTIMATE	CHANCE OF NEEDING REVISIONS
UI ART
SPLASH SCREEN	*3 Antelope faces / *Animation swoosh / *3D Font / *Font Animation / *Final product name	45%	2 days	Game start = fade in company logo, fade out, fade in tools logos, fade out, fade in splash screen with music. Wait for animation to finish, then allow player to tap(or click).			35%
MAIN MENU DEMO LOOP	*List of credits needed / *Scrolling text / *Leaderboard	0%	1/2 day	Game auto switches states in a loop between "Credits", "Leaderboard", and then "Splash Screen", waiting 5 seconds each time before switching.			0%
INFO SCREEN	*Screen layout concept / *Species Distribution / *UI / *Animation & art for interactive elements / *Background drawing	5%	2 days	*Trigger page when player accesses the Animal Compendium(from settings menu or from info button on screen during game)			50%
REWARD SCREEN	*Screen layout concept / *Background drawing	0%	1 day	*Trigger page when player matches new antelopes. The game pauses and screen goes gray, with a picture animating for 3 seconds. Then this goes away(shrinks into the info button) and game unpauses.			50%
VICTORY SCREEN	*Screen layout concept / *Background drawing	0%	1 day	*Trigger page when player wins. The game pauses and screen goes gray, with a picture animating for 5 seconds. Then return to map(still zoomed on same region). That level icon is now gray.			50%
DEFEAT SCREEN	*Screen layout concept / *Background drawing	0%	1 day	*Trigger page when player wins. The game pauses and screen goes gray, with a picture animating for 5 seconds. Then return to map(still zoomed on same region).			50%
TUTORIAL	*Screen layout concept / *PreRendered VFX / *Cursor Texture	0%	1 day	*Show game playing with a cursor animating around to click on everything			50%
SETTINGS MENU	*Text	0%	1/4 day	*Allow player to access a settings menu during game. This pauses the game. / *Mouse over section triggers the text of that section to enlarge and shrink animation			50%
MAP SCREEN	*Animation & art for interactive elements / *Location textures	50%	1 day	*Camera zoom to region. / *5 Nodes that can be set to have a sprite. These nodes will be the locations of levels in that region. / *Randomize animal head pop in and out from behind each node, alternating left and right side. If clicked while lioness there, lioness in level.			50%

CHARACTER AND LEVEL ART
LEVELS	*Location Selections / *Location Design / *World Textures / *Prop textures / *Lighting / *Asset placement	10%	5 days				50%
LIONESS		100%	0 days				25%
HYENA		100%	0 days	*Make Hyena stay on ground after hit. / *Allow player to disable Hyena / *Script node to allow color changes			75%
ANTELOPES	*Remaining Textures / *Fix leg animation	21%	3 days				75%
NPCS	*Sprite textures	5%	4 days				50%